## Sheet1
Task to be completed for Logistic Management System
Table 1
| Task | Start Date | Duration (Day)
| Login to the system | 2022-11-08 | 1
| Customer Registration | 2022-11-09 | 3
| Vehicle Details | 2022-11-12 | 2
| Car Service | 2022-11-14 | 4
| Vehicle Reports | 2022-11-18 | 2
| Payment | 2022-11-20 | 2
| Payment Receipt | 2022-11-21 | 1
| Logout | 2022-11-22 | 4